## Plan Work
Plan Work
Num | Milestone | Missions | Finish date | Status
1 | Start working |  | 13/11/23 | V
2 | Planning the front structure | Components planning, database structure, pages design | 13-14/11/23 | V
3 | Learning technologies | JWT With React | 14-17/11/23 | V
4 |  | React Material UI | 14-17/11/23 | V
5 | Start programing | programing step by step the React App | 18/11/23 | V
6 | Step 1 - initial React App | build all the components and pages | 18-20/11/23 | V
7 | Step 2 - build routes and redux | build the herarchy of routes and add redux to the app | 18-20/11/23 | V
8 | Step 3 - firebase DB | connect app with firebase firestore | 18-20/11/23 | V
9 | Step 4 - Advance Reducer | Split and Combine Reducers with use thunk middleware | 18-20/11/23 | V
10 | Step 5 - Products model | Build the products model | 20-27/11/23 | V
11 | Step 6 - Customers model | Build the customers model | 20-27/11/23 | V
12 | Step 7 - Purchases model | Build the purchases model | 20-27/11/23 | V
13 | Step 8 - Home Page and Statistical calculations | Build the Home Page, and the calculation in the app like amount of purchases products, new products, top selling adv | 28/11/23 | V
14 | Step 9 - Authentication App | Authentication to Firebase with email and password | 29/11/23 | V
15 | Step 10 - Assign roles | Assign admin and regular roles, use service cloud.firestore | 30/11/23 | V
16 | Step 11 - Share components | Improved the display of the parent components, and building sharing between components | 1-2/12/23 | V
17 | Step 12 - improve and sync store data | Improve and Sync between the external DB [Firebase] and the internal DB [redux] | 3-5/12/23 | V
18 | Step 13 - Users collection | authenticate the app with firebase authetication | 5-7/12/2023 | V
19 | Step 14 - optimization | Used memoization hooks for optimizing the performance of my app | 8-9/12/2023 | V
20 | Step 16 - Tests | Perform tests for the application | 2023-12-12 | V
| https://mui.com/material-ui/react-divider/ | Divider
| https://mui.com/material-ui/react-list/ | Lists
Table

## Dependencies
Dependencies
Num | Subject | Module | Usages
|  |  | Relevant File | Imports
1 | Redux | npm install redux | main.jsx | import { legacy_createStore as createStore } from 'redux'
|  | npm install redux-thunk | src/redux/store.js | import { createStore, applyMiddleware } from 'redux'
import thunk from 'redux-thunk'
import rootReducer from './reducers/index'
const store = createStore(rootReducer, applyMiddleware(thunk))
2 | React-Redux | npm install react-redux | main.jsx | import { Provider } from 'react-redux'
import reducer from './redux/rootReducer.js'
const store = createStore(reducer)
ReactDOM.createRoot(document.getElementById('root')).render(
<Provider store={store}>
<App />
</Provider>)
|  |  | A particular component | import { useSelector, useDispatch } from "react-redux";
3 | Routing | npm install react-router-dom | main.jsx | import { BrowserRouter } from 'react-router-dom';
ReactDOM.createRoot(document.getElementById('root')).render(
<BrowserRouter>
<App />
</BrowserRouter>)
|  |  | A particular component | import { Link, useLocation, useNavigate } from 'react-router-dom';
4 | NonSql DB | npm install firebase | firebase.js | import { getFirestore } from 'firebase/firestore';
const db = getFirestore(app);
export default db;
|  |  | A particular component | import { query, collection, onSnapshot, addDoc, deleteDoc, doc } from 'firebase/firestore'
5 | Uuid | npm install uuid | rootReducer.js | import { v4 as uuidv4 } from 'uuid'
6 | sweetalert2 | npm install sweetalert2 | A particular component | import Swal from 'sweetalert2';
import 'sweetalert2/src/sweetalert2.scss';
|  | npm install sass | App.jsx
7 | react-bootstrap-v5 | npm install react-bootstrap-v5 | A particular component | import { Button, Card, Form, Row, Col } from 'react-bootstrap-v5';
8 | axios | npm install axios | utils.js | import axios from 'axios'
9 | mui/material | npm install @mui/material @emotion/react @emotion/styled | Default installation | import Button from '@mui/material/Button'; // Button - For Example
|  | npm install @fontsource/roboto | import it in your entry point | import '@fontsource/roboto/300.css';
import '@fontsource/roboto/400.css';
import '@fontsource/roboto/500.css';
import '@fontsource/roboto/700.css';
|  |  | OR install Roboto through the Google Web Fonts CDN | <link rel="preconnect" href="https://fonts.googleapis.com" />
<link rel="preconnect" href="https://fonts.gstatic.com" crossorigin />
<link
rel="stylesheet"
href="https://fonts.googleapis.com/css2?family=Roboto:wght@300;400;500;600;700&display=swap"
/>
|  | npm install @mui/icons-material | To use the font Icon component, you must first add the Material Icons font: You can do so with npm | npm install @mui/icons-material
|  |  | OR with the Google Web Fonts CDN | <link
rel="stylesheet"
href="https://fonts.googleapis.com/icon?family=Material+Icons"
/>
|  | npm install @mui/x-date-pickers | A particular component
10 | react-jwt | npm install react-jwt | Authentication Components | import { useJwt } from "react-jwt";
const token = "Your JWT";
OR You can also use the methods isExpired(token) and decodeToken(token)
import { isExpired, decodeToken } from "react-jwt";
const token = "Your JWT";
| carousel component | react-slick | npm install react-slick | import Slider from 'react-slick' | It is important to note that the carousel component is provided by the react-slick command, while slick-carousel provides styling for it.
|  | slick-carousel | npm install slick-carousel | slick-carousel provides styling for it
react-material-ui-carousel
| Add timestamp date in react | npm i moment |  | A JavaScript date library for parsing, validating, manipulating, and formatting dates
import moment from 'moment';

## data base structure
designing a Firestore schemas
Collection | Document ID | Document
|  | Field (type) | Validation (rules)
Parent path = / | Parent path = /products | Parent path = /products/document ID
products | unique ID [Example: z29OQxg0r3RnfZgh2iY0] | name :{ type: String } | required | published
|  | price :{ type: number } | required
|  | quantity :{ type: number } | required
|  | description :{ type: String } | required
|  | src :{ type: String } | required
|  | published :{ type: Date } | required
Collection | Document ID | Document
|  | Field (type) | Validation (rules)
Parent path = / | Parent path = /customers | Parent path = /customers/document ID
customers | unique ID [Example: z29OQxg0r3RnfZgh2iY0] | firstName :{ type: String } | required
|  | lastName :{ type: String } | required
|  | city :{ type: String } | required
|  | src :{ type: String } | required
Collection | Document ID | Document
|  | Field (type) | Validation (rules)
Parent path = / | Parent path = /purchases | Parent path = /purchases/document ID
purchases | unique ID [Example: z29OQxg0r3RnfZgh2iY0] | customerID :{ type: String } | required
|  | productID :{ type: String } | required
orderNumber :{ type: timestamp }
|  | date :{ type: timestamp } | required
Collection | Document ID | Document
|  | Field (type) | Validation (rules)
Parent path = / | Parent path = /users | Parent path = /users/document ID
users | unique ID [Example: z29OQxg0r3RnfZgh2iY0] | firstName :{ type: String } | required
|  | lastName :{ type: String } | required
|  | userName :{ type: String } | required
|  | email :{ type: String } | required
*.....*
*.....*

## initial data
Collection | Document ID | Document
|  | Field (type) | Value
Products | unique ID [Example: z29OQxg0r3RnfZgh2iY0] | name :{ type: String } | PC
|  | price :{ type: number } | TV
|  | quantity :{ type: number } | Watch
description :{ type: String }
src :{ type: String }
published :{ type: Date }
Collection | Document ID | Document
|  | Field (type) | Value
Parent path = / | Parent path = /customers | Parent path = /customers/document ID
customers | unique ID [Example: z29OQxg0r3RnfZgh2iY0] | firstName :{ type: String }
lastName :{ type: String }
city :{ type: String }
src :{ type: String }
"Products": [
{
"name": "PC",
"price": "1169",
"quantity": "35",
"description": "laptop with a 15.6 inch screen, Intel® Core™ i7-1255U processor, 8GB internal memory, 512GB SSD drive and no operating system",
"src": "https://media.istockphoto.com/id/1040993610/photo/laptop-online-school.jpg?s=2048x2048&w=is&k=20&c=XyNyguD8VrbcPK_BbdS8HMTxOIlRK9_jxss3NZ1GrwQ="
"published": "20/11/2023"
},
{
"name": "TV",
"price": "999",
"quantity": "40"
"description": "LG UHD TVs upgrade your viewing experience. Enjoy vivid colors and breathtaking details in 4K resolution",
"src": "https://media.istockphoto.com/id/1408422160/photo/close-up-on-mans-hands-at-home-sitting-on-a-couch-in-stylish-loft-apartment-and-playing.jpg?s=2048x2048&w=is&k=20&c=HGkUi30oWszOqS7975cn9F-MvTankvO7SMMq7YBgYRI=",
"published": "22/11/2023"
}
]
"Customers": [
{
"firstName": "Dana",
"lastName": "Live",
"city": "Haifa",
"src": "https://source.unsplash.com/collection/9948714?32"
},
{
"firstName": "Avi",
"lastName": "Cohen",
"city": "Tel Aviv",
"src": "https://source.unsplash.com/collection/9948714?32"
}
]

## Pages
Colors
1
| Bachground |  | Borders
#15162f
#eeeeee
#e9ecec
#b1daff
#1976D2
2
3
4
5
6
7
8
Login Page
Log In
User Name:
________________________
Email:
________________________
Log in
Home Page
Hello, User Name
Products Page
Edit Product Page
Edit Customer Page
Customers Page
Purchases Page
Users Page
Manage Store App
Home
Products
Customers
Purchases
Users
NEW PRODUCTS
{ Name }
Price
Add
{ Name }
Price
Add
{ Name }
Price
Add
{ Name }
Price
Add
{ Name }
Price
Add
TOP SELLING
{ Name }
Price
Add
{ Name }
Price
Add
{ Name }
Price
Add
{ Name }
Price
Add
{ Name }
Price
Add
Amount
total amount of purchased products
Number
{ Name }
Price
<div class: "slick-track">
</div>
Quentity
amount of products in stack
Number
{ Name }
Purchased date
Add
{ Name }
Purchased date
Add
Redirect ----------> "Edit Product"
Redirect ----------> "Edit Customer"
Redirect To Region ----------> "Combobox With All Product"
All Products
Save
Name:
________________________
Price:
________________________
Quentity:
________________________
Update
Delete
Edit Or Delete Product
Customers that bought this product
{ Name }
Purchased date
{ Name }
Purchased date
{ Name }
Purchased date
Products that purchased by this customer
{ Name }
Purchased date
{ Name }
Purchased date
{ Name }
Purchased date
Firdt Name:
________________________
Last Name:
________________________
City:
________________________
Update
Delete
Edit Or Delete Customer
Buy Product
All Products
Buy
Redirect ----------> "Edit Product"
Redirect ----------> "Edit Product"
{ Name }
Redirect ----------> "Edit Customer"
1
2
3
4
1
2
1
2
1
2
3
All Products
Search
All Users
Choosen Date
{ Name }
Redirect ----------> "Edit Product"
Redirect ----------> "Edit Customer"
First Name
Last Name
City
isAdmin
First Name
Last Name
City
isAdmin
LOGIN
Hello, User Name
Hello, User Name
Hello, User Name
Hello, User Name
Hello, User Name
Hello, User Name
New Product
New Customer
New Customer Page
Hello, User Name
New Product Page
Hello, User Name
Firdt Name:
________________________
Last Name:
________________________
City:
________________________
Add
Cancel
Add Customer
Name:
________________________
Price:
________________________
Quentity:
________________________
Add
Cancel
New Product

## Components hierarchy
Pages Component | Components | Models | WS - jsonplaceorder [users] | localStorage | Firebase |  | Redux
[5 empty] | Auth Firebase | FireStore DB | reduce name | initialState | actions | task
App child - [Header] All Routes
LoginPage | LoginPage | usersWS (jsonplaceholder), users (firestore) userLogin (localStorage) | getUserByEmail = { name, username, email, city } | localStorage .setItem("userInfo", name, username, email, city) | createUserWithEmailAndPassword / once signInWithEmailAndPassword | Add a document(await addDoc(collection(db, "users"), obj)) / once | usersReducer | { } | dispatch(login(obj_user)); | store the userLogin into the usersReducer
| Header | userLogin (localStorage) |  | When login: localStorage .setItem("userInfo", name, username, email, city) when logout: localStorage.removeItem('userInfo') |  |  | usersReducer | { } | When login: dispatch(login(obj_user)) dispatch({ type: USER_LOGIN_SUCCESS, payload: user }) When logout: dispatch(logout()) dispatch({ type: USER_LOGOUT }) | store the userLogin into the usersReducer
ProductsPage child - [CardProduct] child - [CardCustomer]
CardProduct
CardCustomer
EditProductPage
CustomersPage
EditCustomerPage
PurchasesPage
UsersPage
HomePage